| Month | Tasks |
| --- | --- |
| March | - Write 1-page summary of proposal - Decide which NSF directorate, division, and program to apply to - Email Program Officer (using OPD template) attaching 1-page summary, and asking for a time to call |
| April | - Identify and contact proposal reviewers, asking if they will review your draft proposal - Complete first draft of Project Narrative |
| May | - Send Draft Project Narrative to reviewers - While waiting for reviews, complete other required documents such as data management plan, biosketch, collaborators and other affiliations, Department letter, etc. - Receive reviews back by end of May |
| June | - Revise based on reviewer feedback - Send Project Summary and Project Narrative to OPD for flow, grammar, stylistic editing - Complete budget - Ask for additional reviewer comments |
| July | - Revise based on additional comments - Begin sending required documents to Sponsored Research Pre-award representative - Submit final packet to Sponsored Research at least 3 days prior to NSF Directorate due date |

CAREER Writing Timeline